AI-Powered Plant Disease Detection and Farmer Assistance Using Generative AI

Capstone Project 7: Project Proposal and Implementation Plan

| Item | Detail |
| --- | --- |
| Version | 1.0, 11 October 2026 |
| Submitted to | Pavan |
| Team | Group 4: Shravanya, Ganesh, Sree Vasthav, Deepa, Priyanshu |
| Repository | GitHub repository to be shared with Pavan as a collaborator (created in Phase 1) |
| UI design | https://www.figma.com/design/jAzrVWopu8ohqh0vKY3ejr/Untitled?node-id=0-1&t=a9ONOMPEykP3iYXF-1 |
| UI prototype | https://www.figma.com/proto/jAzrVWopu8ohqh0vKY3ejr/Untitled?node-id=2-732&p=f&t=fznMf6gxn5W6Fslh-1&scaling=min-zoom&content-scaling=fixed&page-id=0%3A1 |

# 1. Overview and problem statement

Farmers need a simple way to identify plant diseases and act on the result. In this project a farmer uploads an image of a crop. The system detects the disease with a MobileNetV2 model and uses Generative AI to produce a clear explanation and practical treatment advice, and the farmer can ask follow-up questions in a chat.

The primary objective is accurate disease detection with useful recommendations. Support for regional languages, starting with Hindi, is included in our plan as an enhancement.

# 2. Objectives and scope

| Tier | What it includes |
| --- | --- |
| Core | Image upload and instant disease diagnosis with a confidence score. Image quality check that suggests a better photo when needed. Explanations and treatment suggestions generated by an LLM and grounded in an agricultural dataset. A chat interface for follow-up questions, limited to agriculture topics. Testing on real-world images, with metrics reported. |
| Regional language | Hindi explanations and a Hindi user interface, supported by a glossary of agricultural terms. A second regional language if time allows. |

# 3. Dataset

| Dataset | Used for | Notes |
| --- | --- | --- |
| PlantVillage (Kaggle) | Training and testing the disease model | Public dataset of labelled plant leaf images across crops and diseases, as recommended by the coordinator. |
| Agricultural dataset | Grounding the Generative AI | Agricultural terms, disease descriptions and treatment recommendations, with one entry for each disease class the model predicts. Assembled from reliable agricultural sources. |
| Real-world images | Checking performance outside the dataset | Images collected from the internet, as agreed with the coordinator, covering the same crops and diseases as the model. |

Dataset link: kaggle.com/datasets/abdallahalidev/plantvillage-dataset

Preprocessing: resize and scale images consistently, handle tilted or inverted images, reduce noise, and prepare the agricultural text in a consistent format.

# 4. Model selection

## 4.1 Disease detection

MobileNetV2, as preferred in the brief. It is small and fast, which suits a hosted app. We train it on PlantVillage in Colab, evaluate it with a test report including accuracy and F1 score, and then test it on real-world images. If MobileNetV2 does not perform well enough, we will try a ResNet (CNN) model as an alternative. A vision-language model remains an option in the brief but is not planned.

## 4.2 Explanations and treatment suggestions (LLM)

The LLM does not decide the disease. It receives the detected disease and its entry from the agricultural dataset and writes the explanation and advice from that. It is instructed to answer only agriculture-related questions and to decline other topics briefly and politely.

As confirmed by the coordinator, Grok is allowed. We start with the free Grok option and compare other LLMs in the first week, then choose based on answer quality, language support, rate limits and ease of use. The LLM sits behind a simple interface so the provider can be changed without rework.

## 4.3 Regional language pipeline

The explanation is produced in English and then passed through a pipeline: it is summarised with a multilingual BERT-based model, translated with IndicTrans, and then expanded and polished by the LLM. The same pipeline serves English and Hindi through a language parameter. Translation quality is checked using a glossary of agricultural terms, back-translation into English, and comparison with a second translation of the same text.

# 5. System design and technology stack

The solution is a Python stack with a separate API service and user interface. We considered Chainlit and Pydantic AI and chose Streamlit and LangGraph because they match our Figma design and our step-by-step pipeline.

| Component | Choice | Role |
| --- | --- | --- |
| API and core logic | FastAPI | Endpoints for image upload, prediction and chat. It generates interactive API documentation automatically, which we include in the documentation. |
| Agent flow | LangGraph | Models the pipeline as connected steps: image check, prediction, knowledge lookup, LLM explanation and optional translation. It also handles low-confidence and off-topic cases. |
| User interface | Streamlit | Image upload and chat window, built from the Figma design. |
| Disease model | MobileNetV2 on Hugging Face | The trained model is hosted on Hugging Face and called by the API service for predictions. |
| LLM | Grok (free) first, other providers compared | Used behind a provider-independent interface. |
| Containers | Docker Compose with two services | api-service runs FastAPI and the agent. ui-service runs Streamlit and talks to the API over the internal Docker network. |
| Demo | Hosted app and Colab notebook | The hosted app runs live during the presentation, and the notebook supports training and model results. |

## Request flow

- The farmer uploads a crop image in the Streamlit interface.

- The API service checks image quality and asks for a better photo if the image is too blurry, dark or unclear.

- The image is sent to the MobileNetV2 model on Hugging Face, which returns the likely disease and a confidence score. A low score produces a "not sure" response.

- The agent looks up the disease in the agricultural dataset.

- The LLM writes the explanation and treatment advice. If Hindi is selected, the translation pipeline is applied.

- The farmer asks follow-up questions in the chat, which the agent answers within the agriculture topic.

# 6. Challenges and how we address them

| Challenge | Our response |
| --- | --- |
| Image quality, including blurred, low-light, tilted or inverted images | Augmentation and orientation handling during training, consistent image scaling, an image quality check before prediction with a suggestion for a better photo, and a "not sure" response for low confidence. |
| Gap between dataset images and real photos | Testing on real-world images collected from the internet, reporting results next to the dataset results, and trying a ResNet alternative if needed. |
| Accurate translation of agricultural terminology | A glossary of key terms, a translation pipeline using IndicTrans, and automated checks by back-translation and cross-comparison. |
| Keeping the assistant on topic | Instructions that restrict the LLM to agriculture and a short, polite refusal for other subjects. |
| A simple interface for varying digital literacy | Large upload button, short plain-language results, few steps, and a quick test with non-technical users. |

# 7. Evaluation and success criteria

- Disease detection: test report with accuracy, per-class precision, recall and F1 score, and a confusion matrix.

- Real-world images: at least 50% of real-world images predicted correctly in the demo, with the results reported next to the dataset results.

- Explanations: a set of test cases checked for correctness against the agricultural dataset and for clarity.

- Hindi: a sample of translated explanations checked with the glossary, back-translation and a second translation.

# 8. Deliverables

| Deliverable | Contents |
| --- | --- |
| Presentation | Problem statement, dataset, model, approach, challenges, LLM agent, core features, model performance and a live demo. |
| Documentation | Implementation plan, architecture, API documentation, user flow and model results. |
| Git repository | Source code, shared with Pavan (a personal repository is acceptable). |
| Hosted demo | Running application with the user interface, available during the presentation. |
| Colab notebook | Training, evaluation and model results. |

# 9. Implementation plan

The team works across all phases. Phases are sequenced by dependency: the agent flow is built with a placeholder prediction in Phase 2 and switched to our own model in Phase 5. The plan assumes two working weeks and will be adjusted if the final deadline differs.

| Phase | Focus | Key activities | Output | Timing |
| --- | --- | --- | --- | --- |
| 1 | Disease detection model | Create the repository and add collaborators. Train MobileNetV2 on PlantVillage in Colab. Handle tilted and inverted images and scale inputs for efficient training. Image quality check that suggests a better photo. Test on real-world images; target at least 50% correct. Report accuracy and F1; try ResNet if MobileNetV2 falls short. Record challenges and approach. Deploy the model to Hugging Face and hand over to Phase 5. | Trained model, metrics, real-world results, hosted model | Week 1 |
| 2 | LLM agent flow and API | Build the FastAPI service and the LangGraph agent flow that turns a prediction into a diagnosis. Use a placeholder prediction until Phase 5. Restrict the agent to agriculture topics. Compare Grok with other LLMs. Temporary chat interface; full chat working end to end. | Working agent API and chat | Week 1 |
| 3 | Interface and integration | Review the API documentation. Build the final Streamlit interface from the Figma design. Integration testing and sign-off. | Final interface, tested integration | Week 2 |
| 4 | Documentation | Presentation covering the problem, approach, LLM agent, core features and results. Architecture, user flow, implementation plan and API documentation. Model performance section after development. | Presentation and documents | Starts Week 1; final after Phase 5 |
| 5 | Model integration | Replace the placeholder prediction in the agent with our own model. Hugging Face model deployment and inference changes. Check agent output with real predictions. | Agent running on our model | Week 2 |
| 6 | Regional language | Glossary of agricultural terms in English and Hindi. Hindi user interface. Summarise, translate and LLM expansion pipeline, with a language parameter shared with English. Second regional language if time allows. | Hindi support | Week 2 |

# 10. Risks and mitigations

- Model accuracy on real photos. Test early, report the gap, and try ResNet if MobileNetV2 is not enough.

- Hosting. Some free hosts run only a single container, so we confirm that the chosen host supports Docker Compose before relying on it, and keep the Colab notebook as a backup for the demo.

- LLM access and limits. Keep the LLM behind an interface and compare providers in the first week.

- Incorrect treatment advice. Ground answers in the agricultural dataset and include a note to consult a local agricultural expert.

- Translation errors. Use a glossary and automated checks, and keep Hindi as the main language before adding another.

# 11. Coordinator guidance and how it is reflected

| Guidance received | Where it appears |
| --- | --- |
| Use the PlantVillage dataset; prefer MobileNetV2 first and evaluate with a test report including F1 score | Sections 3, 4.1 and 7 |
| Test real-world performance with images from the internet | Sections 3 and 7 |
| At least 50% of images should pass during the demo, along with metrics | Section 7 |
| Submit a presentation, documentation with implementation plan, API documentation and user flow, model results and a Git repository; demo must run hosted while presenting | Sections 5, 8 and 9 |
| Regional language support contributes to full marks | Sections 2 and 4.3, Phase 6 |
| Grok is allowed; explore it and others | Section 4.2, Phase 2 |
| Demo format: hosted app with a UI, and Colab | Sections 5 and 8 |

# Annex A: Task allocation (internal, remove this page before submission)

| Phase | Owner | Notes |
| --- | --- | --- |
| Phase 1: Disease detection model | Ganesh, Shravanya | Colab Pro is available (Ganesh). Hand over the deployed model to Phase 5. |
| Phase 2: LLM agent flow and API | Sree Vasthav, Deepa | Placeholder prediction until Phase 5. |
| Phase 3: Interface and integration | Ganesh | Interface design and integration testing and sign-off. |
| Phase 4: Documentation | Deepa | Starting this week. Model performance and prediction section after development: Shravanya. |
| Phase 5: Model integration | Pruyanshu | Integrate the LLM flow with our own model; Hugging Face deployment of the model and inference changes. |
| Phase 6: Regional language | Entire team | Hindi; one more regional language if possible. |